## Customer Brief
CUSTOMER BRIEF — TechRetail US
Natural language requirements given to Claude · ACP MCP Server translates intent → governed provisioning actions
⚠ DATA MASKING NOTICE
This workbook was used as the source of truth for an AI-driven provisioning session on a Cisco Webex Contact Center sandbox (Cisco dCloud). Claude — acting through the ACP MCP Server — read this workbook, decomposed the requirements into API tool calls, and provisioned the environment entirely through natural language interaction. The following values were real sandbox inputs that Claude used during provisioning. They have been masked in this public version to prevent misuse: • PSTN DID numbers (assigned to the sandbox entry points) → replaced with +1-XXX-XXX-0001 / +1-XXX-XXX-0002 • Sandbox org name and agent email addresses → replaced with <your-sandbox-org> / <your-sandbox>.wbx.ai All other content — queue designs, IVR flow logic, tool sequences, integration specs — is genuine and reflects what was provisioned.
1 · COMPANY SNAPSHOT
Company | TechRetail Inc. | Industry: Consumer Electronics Retail
Region | United States (East Coast primary) | Employees: ~4,200 (400 in customer-facing roles)
CC Platform | Cisco Webex Contact Center (cloud) | Deployment: Greenfield — no prior CC platform
Simulation env | Cisco dCloud sandbox (non-production) | Goal: POC — prove AI-driven provisioning end-to-end
2 · WHAT THE CUSTOMER ASKED FOR (natural language brief given to Claude)
We are TechRetail — a US consumer electronics retailer. We want to set up a brand-new contact center on Cisco Webex CC without manually clicking through Control Hub. We need two call queues — one for Sales (orders, pricing, bulk enquiries) and one for Support (product faults, returns, exchanges). Calls should be answered by an IVR that greets the customer, checks business hours, lets them say or press their choice, and deflects common FAQs to a bot before routing to a live agent. We also want our Zendesk CRM to pop the customer record on the agent screen the moment a call is answered, and for post-call AI summaries to be written back to the Zendesk ticket automatically. Agent Assist should suggest KB articles during the call. All of this should happen through natural language — we describe what we want, Claude figures out the API calls, shows us the plan, waits for our approval, then provisions everything in sequence. Every action must be logged for audit.
3 · FUNCTIONAL REQUIREMENTS (extracted by Claude from the brief)
Requirement | Detail | Priority
Two skills-based queues | TechRetail-Sales (skills: sales, billing) and TechRetail-Support (skills: technical, product). SLA 80% in 30 s / 45 s. | MUST
IVR with DTMF + speech | Welcome prompt → Business hours check → Intent collector (press 1/Sales, press 2/Support) → Retry on no-input → Fallback queue. | MUST
AI disclosure in welcome | Inform caller they may interact with AI and can request a human at any time. (EU AI Act Art 50 best practice, applied even in US sandbox.) | MUST
Dialogflow CX bot deflection | Sales bot: order_status, pricing, bulk_order. Support bot: product_fault, returns, exchange. Escalate to human on no-match. | SHOULD
Zendesk CRM screen pop | On call answer — POST caller number to Zendesk, return customer name + ticket ID to agent desktop widget. | SHOULD
AI Call Summary → Zendesk | Post-call AI summary written to Zendesk ticket on agent wrap-up. | SHOULD
Agent Assist | Live KB article suggestions shown to agent during the call. | SHOULD
Approval gate on every write | Claude presents the full provisioning plan. Admin approves before any API write executes. Every action logged to audit trail. | MUST
Call recording | Record all calls — confirm already enabled before provisioning sequence begins. | DONE
4 · CONSTRAINTS
Zero manual clicks in Control Hub | All provisioning via Claude natural language → ACP tool calls only. The only manual step: initial OAuth consent in browser.
Audit trail mandatory | Every write tool logs: timestamp, tool name, payload, approval status, outcome.
Sandbox only | POC on Cisco dCloud. No production tenant. Sandbox credentials anonymised for public sharing (see masking notice above).
Approval before every write | ACP governance layer: no write executes without explicit human approval in Claude Desktop.
Skills before queues | Provisioning sequence enforced: skills → queues → flow → publish → entry point. Order violations rejected.
Claude (claude-sonnet-4-6) · ACP v1.0 · github.com/Rajmohan80/claude-mcp-cc-provisioning

## Overview
TechRetail US — Webex CC Design Workbook
Greenfield simulation ¦ Sandbox: <your-sandbox-org> ¦ Rajmohan Mangattu ¦ CCIE #55207
SANDBOX INVENTORY — What Exists Today
Item | Current Value | Status | Notes
Org / Tenant Name | <your-sandbox-org> | Active | US region, Cisco sandbox
Admin Account | admin@<your-sandbox>.wbx.ai | Active | Full admin rights
Agent 1 | user1@<your-sandbox>.wbx.ai | Active | Premium Agent, Ext 1001
Agent 2 / Supervisor | user2@<your-sandbox>.wbx.ai | Active | Supervisor, Ext 1002
PSTN DID | +1-XXX-XXX-0001 | Active | Assigned to Contact Center entry point
Spare DID | +1-XXX-XXX-0002 | Active | Available — not mapped yet
Entry Point | Entry Point-1 (Inbound Telephony) | Active | Mapped to +1-XXX-XXX-0001
Queue | Queue-1 (Inbound, Teams, Telephony) | Active | Default, no skills-based
Outdial Queue | Outdial Queue | Active | System generated
Flow | BasicQueueFlow | Active | Simple queue flow, no AI
Site | Site-1 | Active | Default_Multimedia_Profile
Team | Sandbox Team Agent | Active | Both agents assigned
Voice Platform | Real Time Media Service | Active | Webex Calling telephony
Call Recording | Enabled | Active | Record all calls = ON
Concurrent Voice | 60 licenses | Active | Surge 30%, Max 78 concurrent
DESIGN TARGET — TechRetail US Greenfield Simulation
Component | Design Decision | API Provisionable? | Block | Status
Sales Queue | TechRetail-Sales ¦ Skills: sales, billing ¦ Inbound Telephony ¦ Teams assignment | YES — Block 7 | Block 7 | PLANNED
Support Queue | TechRetail-Support ¦ Skills: technical, product ¦ Inbound Telephony ¦ Teams assignment | YES — Block 7 | Block 7 | PLANNED
IVR Flow | Welcome → NLU intent → Dialogflow CX bot → Escalate → Route queue → Queue music | YES — Block 7 | Block 7 | PLANNED
Entry Point Mapping | +1-XXX-XXX-0001 → TechRetail-MainFlow | YES — Block 7 | Block 7 | PLANNED
+1-XXX-XXX-0002 DID | Map to TechRetail-Support entry point (spare DID) | YES — Block 7 | Block 7 | PLANNED
Skills Definition | sales, billing, technical, product — mapped to agents | YES — Block 7 | Block 7 | PLANNED
Dialogflow CX | FAQ bot: order status, product queries, callback request — GCP project-voice-ccai | PARTIAL — GCP | Block 8 | PLANNED
Agent Assist | Enable KB suggestions during calls — toggle via desktop profile API | YES — Block 6F | Block 6F | PLANNED
AI Call Summary | Post-call summary — toggle at tenant level via API | YES — Block 6F | Block 6F | PLANNED
Zendesk Screen Pop | HTTP Request node in flow — POST ANI to Zendesk → return ticket ID | YES — Block 6E | Block 6E | PLANNED
Call Recording | Already ON — record all calls enabled | DONE | Block 6A | DONE
EU Art 50 Disclosure | AI disclosure in welcome prompt (US sandbox — best practice) | YES — Flow node | Block 7 | PLANNED

## Queue Design
Queue Design — TechRetail US
Two inbound queues with skills-based routing ¦ ACP MCP tool: create_wxcc_queue
Parameter | TechRetail-Sales | TechRetail-Support | Queue-1 (Existing) | Notes
Queue Name | TechRetail-Sales | TechRetail-Support | Queue-1 | Exact name for API call
Channel Type | telephony | telephony | telephony | TELEPHONY in API
Contact Direction | INBOUND | INBOUND | INBOUND
Skills-Based Routing | YES | YES | NO | Enable in API payload
Agent Assignment | Teams | Teams | Teams | Team-based assignment
Service Level % | 80% | 80% | Not set | SL threshold
Service Level (sec) | 30 | 45 | Not set | Seconds
Max Wait Time (sec) | 300 | 480 | Not set | 5 min Sales, 8 min Support
Music on Hold | Default | Default | Default | Use existing MOH file
Team Assignment | Sandbox Team Agent | Sandbox Team Agent | Sandbox Team Agent | Both teams same in sandbox
Skills Required | sales, billing | technical, product | None | Define skill profiles first
Primary Agent | User1 Agent1 | User1 Agent1 | Both | Both agents handle both queues
Supervisor | User2 Agent2 | User2 Agent2 | User2 Agent2
ACP Tool | create_wxcc_queue | create_wxcc_queue | SKIP (exists) | Block 7 write tool
Approval Required | YES | YES | N/A | Approval gate before API call
Status | PLANNED | PLANNED | ACTIVE
SKILLS DEFINITION — Must be created before queues
Skill Name | Type | Queue | Assigned To | ACP Tool
sales | Proficiency | TechRetail-Sales | User1 Agent1 | create_wxcc_skill
billing | Proficiency | TechRetail-Sales | User1 Agent1 | create_wxcc_skill
technical | Proficiency | TechRetail-Support | User1 Agent1 | create_wxcc_skill
product | Proficiency | TechRetail-Support | User1 Agent1 | create_wxcc_skill

## IVR Flow Design
IVR Flow Design — TechRetail-MainFlow
ACP MCP tool: generate_wxcc_flow → import_wxcc_flow → map_entrypoint_flow
FLOW NODE SEQUENCE — TechRetail-MainFlow
Step | Node Type | Configuration | Success Path | Failure Path | Notes
1 | Start / Entry | Entry Point: +1-XXX-XXX-0001 → TechRetail-MainFlow | Step 2 | — | Call arrives
2 | AI Disclosure (Art 50) | Play prompt: 'This call may be handled by AI. You may request a human agent at any time.' | Step 3 | Step 3 | EU AI Act Art 50 — best practice even for US
3 | Business Hours Check | Schedule: Mon-Fri 09:00-18:00 EST ¦ Holiday list: US Federal | Step 4 (open) | Step 14 (closed)
4 | Welcome Prompt | Play: 'Welcome to TechRetail. For Sales press 1 or say Sales. For Support press 2 or say Support.' | Step 5 | Step 6 (timeout) | DTMF + speech hybrid
5 | Intent Collector | Collect DTMF digit OR speech input ¦ Timeout 5 seconds ¦ Retry 2 times | Step 7 | Step 6
6 | No Input Handler | Play: 'We did not receive your selection.' ¦ Route to default queue | Queue-1 | Step 14 | Fallback
7 | Intent Router | Digit 1 OR speech 'sales' → Sales ¦ Digit 2 OR speech 'support' → Support | Step 8 or 9 | Step 6
8 | Dialogflow CX (Sales) | VAV2 node ¦ CCAI Config: TechRetail-Sales-Bot ¦ FAQ: orders, pricing, bulk | Step 10 | Step 11 (escalate) | Needs CCAI connector registered
9 | Dialogflow CX (Support) | VAV2 node ¦ CCAI Config: TechRetail-Support-Bot ¦ FAQ: product, fault, returns | Step 12 | Step 13 (escalate)
10 | Sales Queue | Queue: TechRetail-Sales ¦ Music: default ¦ Callback offer at 2 min | Agent answers | Step 14
11 | Sales Escalate | Play: 'Connecting you to a Sales agent.' → Queue TechRetail-Sales | Step 10 | Step 14 | Bot escalation path
12 | Support Queue | Queue: TechRetail-Support ¦ Music: default ¦ Callback offer at 4 min | Agent answers | Step 14
13 | Support Escalate | Play: 'Connecting you to a Support agent.' → Queue TechRetail-Support | Step 12 | Step 14 | Bot escalation path
14 | After Hours / Error | Play: 'Our office is closed. Hours: Mon-Fri 9am-6pm EST. Please call back.' ¦ Disconnect | End | End
ENTRY POINT MAPPING
DID | Entry Point Name | Flow | Channel Type | ACP Tool | Status
+1-XXX-XXX-0001 | Entry Point-1 | TechRetail-MainFlow | TELEPHONY | map_entrypoint_flow | PLANNED
+1-XXX-XXX-0002 | TechRetail-Support-EP | TechRetail-MainFlow | TELEPHONY | create_entry_point | PLANNED

## MCP Tool Plan
ACP MCP Tool Plan — Block 7 Provisioning
Every tool call goes through ACP governance ¦ Approval gate before every write
PROVISIONING SEQUENCE — Order matters. Skills before queues. Queues before flows. Flows before entry points.
Seq | ACP Tool | What It Does | WxCC API Endpoint | Scope Required | Approval Gate | Block
1 | get_wxcc_queue_stats | Read existing queues — confirm baseline before writing | GET /search (GraphQL) | knowledge:read | NO | Block 6A ✓
2 | get_wxcc_agent_list | Read agents — confirm user1, user2 exist | GET /organization/{id}/user | knowledge:read | NO | Block 6A ✓
3 | get_wxcc_routing_recommendation | Read entry points and recommend routing | GraphQL + REST | diagnostics:run | NO | Block 6A ✓
4 | create_wxcc_skill | Create skill: sales | POST /organization/{id}/skill | actions:execute | YES | Block 7
5 | create_wxcc_skill | Create skill: billing | POST /organization/{id}/skill | actions:execute | YES | Block 7
6 | create_wxcc_skill | Create skill: technical | POST /organization/{id}/skill | actions:execute | YES | Block 7
7 | create_wxcc_skill | Create skill: product | POST /organization/{id}/skill | actions:execute | YES | Block 7
8 | create_wxcc_queue | Create TechRetail-Sales queue (skills-based) | POST /organization/{id}/queue | actions:execute | YES | Block 7
9 | create_wxcc_queue | Create TechRetail-Support queue (skills-based) | POST /organization/{id}/queue | actions:execute | YES | Block 7
10 | generate_wxcc_flow | LLM generates TechRetail-MainFlow JSON from spec | Internal — LLM generation | actions:execute | YES | Block 7
11 | import_wxcc_flow | Import generated flow JSON to WxCC | POST /organization/{id}/flow | actions:execute | YES | Block 7
12 | publish_wxcc_flow | Publish flow — makes it live | POST /flow/{id}/publish | actions:execute | YES | Block 7
13 | map_entrypoint_flow | Map +1-XXX-XXX-0001 entry point to TechRetail-MainFlow | PATCH /organization/{id}/entryPoint | actions:execute | YES | Block 7
14 | enable_agent_assist | Enable Agent Assist on desktop profile | PATCH /organization/{id}/desktopProfile | actions:execute | YES | Block 6F
15 | enable_call_summary | Enable AI Call Summary at tenant level | PATCH /organization/{id}/features | actions:execute | YES | Block 6F
APPROVAL GATE DESIGN: Supervisor/admin types a provisioning request in Claude Desktop. ACP decomposes into steps 4-13 above and presents the full plan. Admin approves. ACP executes each write tool in sequence. Every call logged to audit.readable.log. Claude Desktop shows confirmation after each step.

## Integration Map
Integration Map — Third-Party Systems
Dialogflow CX ¦ Zendesk CRM ¦ Splunk Observability ¦ n8n Automation
Dialogflow CX
Integration Type | Google CCAI Connector → VAV2 node in Flow Designer
GCP Project | project-voice-ccai (to be created)
Region | us-central1 (closest to US1 WxCC DC)
Bot: Sales | TechRetail-Sales-Bot ¦ Intents: order_status, pricing, bulk_order
Bot: Support | TechRetail-Support-Bot ¦ Intents: product_fault, returns, exchange
Handoff Variable | virtualAgentResult → escalated → route to human queue
EU Art 50 | Welcome message includes AI disclosure before VAV2 activity
ACP Tool | create_ccai_config, update_flow_with_vav2
Block | Block 8
Status | PLANNED — GCP project-voice-ccai not yet created
Zendesk CRM
Integration Type | HTTP Request node in Flow → Zendesk REST API
Trigger | On call answer — POST caller ANI to Zendesk
Screen Pop | Return ticket ID + customer name → Agent Desktop widget
Ticket Creation | On wrap-up — POST call summary to Zendesk ticket
Call Summary | AI-generated by Cisco AI Call Summary feature
Zendesk API | POST /api/v2/tickets ¦ Authorization: Bearer {ZENDESK_TOKEN}
ACP Tool | configure_crm_screenpop, create_zendesk_ticket
Block | Block 6E
Status | PLANNED — Zendesk tenant needed
Splunk Observability
Integration Type | ACP audit events → Splunk HTTP Event Collector (HEC)
Data Source | audit.readable.log + RAGAS scores + agent traces
Dashboard | Queue SLA ¦ Governance events ¦ Model health scores
Alert | RAGAS context_precision < 0.85 → alert fires
Splunk Tier | Free tier — 500MB/day (sufficient for lab)
ACP Tool | No tool — n8n ships events to Splunk HEC endpoint
Block | Block 10
Status | PLANNED
n8n Automation
Integration Type | Workflow automation — schedule + event-driven
Workflow 1 | Every commit → run RAGAS golden set → write scores to log
Workflow 2 | Every 15 min → call get_wxcc_queue_stats → ship to Splunk
Workflow 3 | RAGAS score drop → trigger Splunk alert → notify Teams
Workflow 4 | Token expiry (14 days) → run get_wxcc_token.py → update .env
ACP Connection | n8n HTTP node → POST http://localhost:<ACP_PORT>/mcp/
Block | Block 10
Status | PLANNED

## Block Plan
Build Block Plan — Full Portfolio Roadmap
Each block maps to a domain ¦ Author: Rajmohan Mangattu ¦ CCIE Collaboration #55207
Block | Name | What Gets Built | Domains Covered | Status
1-4 | ACP Core | OAuth issuer, MCP gateway, control_hub.yaml policy, audit trail, 5 governed tools | D2, D6 | DONE ✓
5 | A2A Caller | Groq picks tool → calls ACP over real MCP → prose answer → audit proof | D2, D4 | DONE ✓
6A | Live WxCC API | Authorization Code OAuth, 7 API functions (REST + GraphQL), schema verified | D1, D5 | DONE ✓
6B | WxCC Tools in MCP | 3 governed tools registered: queue_stats, agent_list, routing_rec — 5/5 governance checks | D1, D2, D5 | DONE ✓
6C | Claude Desktop | mcp-remote bridge, ACP connected, hammer icon visible | D2, D3 | DONE ✓
6D | Service Token | Auto-minted service token — zero credential friction from Claude Desktop | D2, D6 | DONE ✓
6E | Zendesk CRM | HTTP Request node → Zendesk API → screen pop on answer, ticket on wrap-up | D1, D5 | PLANNED
6F | Agent Assist + Summary | Enable Agent Assist and AI Call Summary via desktop profile API | D1, D5 | PLANNED
7 | Provisioning + Gate | create_queue, generate_flow, import_flow, map_entrypoint ¦ Approval gate ¦ Full Domain 3 demo | D2, D3, D6 | NEXT
8 | Voice Front End | Dialogflow CX answers call ¦ ACP backend ¦ EU Art 50 disclosure ¦ GCP project-voice-ccai | D1, D5 | PLANNED
9 | Network Diagnostics | 4 agents: path, SD-WAN, QoS, SIP ¦ Correlator → ranked hypothesis ¦ CML build | D4 | PLANNED
10 | Observability Rails | n8n RAGAS CI ¦ Splunk dashboard ¦ Token auto-refresh ¦ Full platform health view | D7 | PLANNED